## Sheet1
FRONTEND TEAM- team leader joy
Date | TEAM LEADER |  | TEAM A |  | TEAM B
| KOMMALA JOY BENJAMIN |  | Kavya&Sowmya |  | SHWETA&BHUVANESHWARI
2022-02-14 | Day 1 | Work On Home Page | Day 1 | Work On View Order Page | Day 1 | Work On Adminlogin Services
2022-02-15 | Day 2 | Work On AdminLogin, User Login, Signup Pages | Day 2 | Work On Available Products | Day 2 | Work On User Login Registration Services
2022-02-16 | Day 3 | Work On Admin Page, User Page, Manage Products | Day 3 | Work On Gathering Components and Modification Of available Products | Day 3 | Work On Gathering Components
2022-02-17 | Day 4 | Work On Routing Pages | Day 4 | Work On About Us Page | Day 4 | Work On Contact Page
2022-02-18 | Day 5 | Work On Services | Day 5 | Work On Add View Order Page | Day 5 | Work On Cart Page
2022-02-19 | Day6 | work on modifications | Day6 | Work On Categories Page | Day6 | Work On Categories Page
2022-02-21 | Day7 | working on services | Day7 | Work On Services | Day7 | Work On Services
2022-02-22 | Day 8 | Work On Integration | Day8 | Work on Antipyretics | Day 8 | Work On Antibiotics Pages
2022-02-23 | Day9 | Work On Integration | Day9 | Work On Documentation | Day 9 | Work On Documentation
2022-02-24 | Day10 | Work On Integration | Day10 | Work On PPT | Day 10 | Work On Documentation
BACKEND TEAM- team leader ajay
Date | TEAM A |  | TEAM B |  | TEAM C
| AJAY&ADESH |  | CHAYA&RUSHITHA |  | ANKUSH&SUHAS
2022-02-14 | Day 1 | Work On Medicine list,modules&package creation | Day 1 | work on admin login modules and package creation | Day 1 | work on userlogin modules and package creation
2022-02-15 | Day 2 | checking the functionalities of written code | Day 2 | checking the functionalities of written code | Day 2 | checking the functionalities of written code
2022-02-16 | Day 3 | work on user registration modules creation&checking the functionality | Day 3 | testing with postman&bug removing | Day 3 | testing with postman&bug removing
2022-02-17 | Day 4 | testing with the postman | Day 4 | work on cart module creation | Day 4 | testing cart module with postman
2022-02-18 | Day 5 | Work On creating order list | Day 5 | testing cart module with postman | Day 5 | testing orderlist on postman
2022-02-19 | Day 6 | working on testing | Day 6 | working on testing | Day 6 | working on testing
2022-02-21 | Day 7 | work on testing backend code | Day 7 | work on testing backend code | Day 7 | work on testing backend code
2022-02-22 | Day 8 | Work On Cart and Order Testcases | Day 8 | Work On Admin and User Login Pages | Day 8 | Work On Medicine and User SignUp Pages
2022-02-23 | Day 9 | Work On Integration | Day 9 | Rushitha: Work On Documentation, Chaya: | Day 9 | Work On Validations
2022-02-24 | Day 10 | Work On Integration | Day 10 | Rushitha:Work On PPT, Chaya: Work On Integration | Day 10 | Work On Integration